## Clarification Log
Clarifications log: Tender for the provision of temporary structure at ReActon circular economy hub for West London Waste Authority (Ref: WLWA/SS029/2026)
Date Received | Subject | Tenderers Question | WLWA Response | Response date
2023-12-15 | ITT / Method Statement | 1. In section 7.4 “Bidders must respond to all of the questions in e-tendering response questionnaires.” Is the format to follow the WEEE - WLWA ITT, 8.8 Evaluation Questions format sectioned into the different Method Statements and/or Annex 2? As there is no response document provided. | WLWA would like bidders to submit responses to the method statement questions as detailed in section 8.8 Evaluation Questions of the ITT as part of their submission. There is no separate document / questionnaire to complete.
|  | 2. In section 7.12 “Provisional lists of the Third-Party Employees are contained in Schedule 5.”. We cannot locate the provisional list, please advise. | This is not relevant to his contract and we have removed this reference from the terms and conditions.
2023-12-15 |  | Good afternoon, Please find attached Veolia Legal Commentary/Clarifications Table. Kind regards The Bid Team | NA
2026-07-02 | Annex 1 - Scope | I have reviewed the documents & cannot see any mention of the size of units required or the intended layouts. Could you provide please & I can take a look. | The authority has not prescribed specific unit sizes or a fixed site layout, as we wish to encourage innovation and allow bidders to develop the solution they consider best meets the project objectives. Bidders should note that planning permission allows for up to 16 single story shipping containers/modular units, and proposals must remain compliant with the approved planning parameters and all requirements set out within the tender documentation. It is for bidders to determine the appropriate mix, size and arrangement of units required to deliver a functional, adaptable and attractive circular economy hub. The proposed layout and rationale should be clearly demonstrated within the tendency submission. | 2026-07-02