## Clarification Log
Clarifications log: Tender for the provision of temporary structure at ReActon circular economy hub for West London Waste Authority (Ref: WLWA/SS029/2026)
Date Received | Subject | Tenderers Question | WLWA Response | Response date
2023-12-15 | ITT / Method Statement | 1. In section 7.4 “Bidders must respond to all of the questions in e-tendering response questionnaires.” Is the format to follow the WEEE - WLWA ITT, 8.8 Evaluation Questions format sectioned into the different Method Statements and/or Annex 2? As there is no response document provided. | WLWA would like bidders to submit responses to the method statement questions as detailed in section 8.8 Evaluation Questions of the ITT as part of their submission. There is no separate document / questionnaire to complete.
|  | 2. In section 7.12 “Provisional lists of the Third-Party Employees are contained in Schedule 5.”. We cannot locate the provisional list, please advise. | This is not relevant to his contract and we have removed this reference from the terms and conditions.
2023-12-15 |  | Good afternoon, Please find attached Veolia Legal Commentary/Clarifications Table. Kind regards The Bid Team | NA
2026-07-02 | Annex 1 - Scope | I have reviewed the documents & cannot see any mention of the size of units required or the intended layouts. Could you provide please & I can take a look. | The authority has not prescribed specific unit sizes or a fixed site layout, as we wish to encourage innovation and allow bidders to develop the solution they consider best meets the project objectives. Bidders should note that planning permission allows for up to 16 single story shipping containers/modular units, and proposals must remain compliant with the approved planning parameters and all requirements set out within the tender documentation. It is for bidders to determine the appropriate mix, size and arrangement of units required to deliver a functional, adaptable and attractive circular economy hub. The proposed layout and rationale should be clearly demonstrated within the tendency submission. | 2026-07-02
2026-07-02 | Annex 1 - Scope | Schedule 1 - Planning Permission (TBC) Schedule 3 - Draft Layout (TBC) Please can you confirm when these documents will be available. | Thank you for your patience these documents are now available to be shared. | 2026-07-07
2026-07-06 | Annex 1 - Scope | You ask for temporary buildings but as they are to be on site for 5 years they should meet building regulations. Can you please advise if you require the units to meet building regs or not? | The modular buildings shall comply with all applicable Building Regulations and other statutory requirements relevant to the proposed use. It is the bidders responsibility to ensure that their proposed solution is fully compliant. | 2026-07-07
2026-07-06 | Annex 1 - Scope , Schedule 1 | Planning permission: This is currently marked "TBC" Please could you provide the planning decision notice and full conditions, so that our design proposal can be checked for compliance before submission. | Thank you for your patience these documents are now available to be shared. | 2026-07-07
2026-07-06 | Annex 1 -Scope , Schedule 3 | This is also marked "TBC," yet Annex 1 Section 4 states "a draft layout is provided at Schedule 3" and invites bidders to refine it. Please could you confirm whether a draft layout exists and, if so, provide it as a matter of priority. If no layout is being provided, please confirm that Section 4 should be read on that basis | Thank you for your patience these documents are now available to be shared. | 2026-07-07