## Clarification Log
Clarifications log: Tender for the provision of temporary structure at ReActon circular economy hub for West London Waste Authority (Ref: WLWA/SS029/2026)
Date Received | Subject | Tenderers Question | WLWA Response | Response date
2023-12-15 | ITT / Method Statement | 1. In section 7.4 “Bidders must respond to all of the questions in e-tendering response questionnaires.” Is the format to follow the WEEE - WLWA ITT, 8.8 Evaluation Questions format sectioned into the different Method Statements and/or Annex 2? As there is no response document provided. | WLWA would like bidders to submit responses to the method statement questions as detailed in section 8.8 Evaluation Questions of the ITT as part of their submission. There is no separate document / questionnaire to complete.
|  | 2. In section 7.12 “Provisional lists of the Third-Party Employees are contained in Schedule 5.”. We cannot locate the provisional list, please advise. | This is not relevant to his contract and we have removed this reference from the terms and conditions.
2023-12-15 |  | Good afternoon, Please find attached Veolia Legal Commentary/Clarifications Table. Kind regards The Bid Team | NA
2026-07-02 | Annex 1 - Scope | I have reviewed the documents & cannot see any mention of the size of units required or the intended layouts. Could you provide please & I can take a look. | The authority has not prescribed specific unit sizes or a fixed site layout, as we wish to encourage innovation and allow bidders to develop the solution they consider best meets the project objectives. Bidders should note that planning permission allows for up to 16 single story shipping containers/modular units, and proposals must remain compliant with the approved planning parameters and all requirements set out within the tender documentation. It is for bidders to determine the appropriate mix, size and arrangement of units required to deliver a functional, adaptable and attractive circular economy hub. The proposed layout and rationale should be clearly demonstrated within the tendency submission. | 2026-07-02
2026-07-02 | Annex 1 - Scope | Schedule 1 - Planning Permission (TBC) Schedule 3 - Draft Layout (TBC) Please can you confirm when these documents will be available. | Thank you for your patience these documents are now available to be shared. | 2026-07-07
2026-07-06 | Annex 1 - Scope | You ask for temporary buildings but as they are to be on site for 5 years they should meet building regulations. Can you please advise if you require the units to meet building regs or not? | The modular buildings shall comply with all applicable Building Regulations and other statutory requirements relevant to the proposed use. It is the bidders responsibility to ensure that their proposed solution is fully compliant. | 2026-07-07
2026-07-06 | Annex 1 - Scope , Schedule 1 | Planning permission: This is currently marked "TBC" Please could you provide the planning decision notice and full conditions, so that our design proposal can be checked for compliance before submission. | Thank you for your patience these documents are now available to be shared. | 2026-07-07
2026-07-06 | Annex 1 -Scope , Schedule 3 | This is also marked "TBC," yet Annex 1 Section 4 states "a draft layout is provided at Schedule 3" and invites bidders to refine it. Please could you confirm whether a draft layout exists and, if so, provide it as a matter of priority. If no layout is being provided, please confirm that Section 4 should be read on that basis | Thank you for your patience these documents are now available to be shared. | 2026-07-07
2026-07-10 | Annex 1 - Scope / Planning Permission | Planning permission 250683FUL ties the development to a specific set of approved drawings (Condition 2). Please could you confirm the degree of flexibility bidders have to propose a reconfigured site layout as part of their tender — specifically, would a layout that varies from the approved drawings require a further planning submission (e.g. a non-material amendment or a minor material/s73 application) before it could be constructed, or would variation within the existing consented footprint and access arrangement be acceptable without further consent? | Tenderers should base their proposals on the approved planning permission and associated drawings however, the authority recognises that there may be limited scope for minor adjustments to the positioning and configuration of the buildings and associated infrastructure, provided these remain consistent with the overall approved development and do not constitute a material departure from the planning permission. Where a tenderer proposes an alternative design or layout, this should be clearly identified within the tender submission. The Authority will assess any proposed variation on its merits and determine whether a planning amendment is required. Depending on the nature and extent of the proposed changes this may comprise a non- material amendment, a section 73 application or where changes are more substantial or fresh planning application. | 2026-07-15
2026-07-10 | Annex 1 Scope / Planning Permission | Please could you confirm who would bear responsibility, in time and cost, for securing any planning amendment that may be necessitated by an innovative bid design departing from the currently approved layout. We note Clause 20.6 of the amended Conditions of Contract excludes only Consents “already identified and obtained before the Contract Date” from the Contractor's general obligation to obtain Consents, and it is not clear how this applies to a design-driven variation of the existing permission | Tenderers should base their proposals on the approved planning permission and associated drawings. Where a Tenderer proposes an alternative design that requires a planning amendment, this should be clearly identified within the tender submission. Where the Authority agrees to pursue such an amendment, the authority will be responsible for securing and funding any associated planning application. Tenders should not include the cost of any planning application or planning amendment within their tendered price. | 2026-07-15
2026-07-10 | Annex 3 - Pricing Schedule | The Work Package lines in Annex 3 (Training & Workshop Space, Delivery Partner Workshop, Tenant Workshop, Shop, Tenant Office Units (4 No.), Storage Units (5 No.), and Welfare Facility) account for 14 container/modular units, against the 16-unit cap confirmed in both the Scope and the planning permission. Two required elements do not appear to have a corresponding Work Package line: (a) the Food Distribution Area (a functional requirement under Annex 1, Section 5) and (b) cycle/bicycle storage (required under planning Condition 3 – 4 secure cycle spaces prior to first occupation). Please could you confirm which Work Package these should be priced under, or whether dedicated lines will be added to a reissued Pricing Schedule. | The food distribution area does not form part of the current phase or works and should not be included within the Contractor's tendered price. The provision of cycle storage will be managed and implemented separately by the Authority and should also be excluded from the pricing schedule. No amendment to the pricing schedule will therefore be issued in respect of these items. | 2026-07-15
2026-07-10 | Annex 2a/b - Terms and Conditions | "Defect" is defined under the amended Clause 11.2(4) by reference to compliance with "the Scope," and certain functional requirements in Annex 1, Section 5 are drafted at a high level. Would the Authority consider issuing a short addendum setting out clear headline deliverables against each Work Package, aligned to the Pricing Schedule, to reduce ambiguity for both parties as to what constitutes satisfactory completion? | The Authority considers that the tender documentation provides sufficient information for tenderers to understand the required deliverables and completion criteria for each Work Package. The procurement has been structured on a design-and-build basis and tenderers are expected to develop and deliver a complete solution that meets the requirements of the Scope and the Contract. Accordingly, the Authority does not intend to issue a separate addendum setting out additional deliverables or completion criteria for each Work Package. Tenderers should base their submission on the Scope, Specification, Pricing Schedule and associated tender documents, which should be read as a whole. Should any specific ambiguity remain, tenderers are invited to raise further clarification responses prior to the clarification deadline. | 2026-07-15
2026-07-10 | Annex 1 - Scope | Annex 1 confirms that payment is only triggered on satisfactory completion of a Work Package, with no provision for advance or mobilisation payment. Given that works such as container procurement and conversion require significant contractor expenditure in advance of any Work Package being capable of completion, would the Authority consider restructuring one or more Work Packages into interim milestones (for example, "materials procured/on order" and "installed and commissioned") to better align payment timing with contractor cash flow, within the existing payment mechanism? | The authority acknowledges the importance of contractor cash flow and has considered the proposed approach. However, the payment mechanism will remain as set out in the tender documentation and will not be amended to introduce additional interim milestones or mobilisation payments. Tenderers should price and programme the works on the basis of the existing work packages and associated payment arrangements. The authority considers that the current structure provides an appropriate balance between commercial certainty and the achievement of clearly defined deliverables. | 2026-07-15
2026-07-10 | Annex 2a/b Terms and Conditions | Please could you confirm whether the Housing Grants, Construction and Regeneration Act 1996 applies to this contract. The Client's Contract Data states that it does not apply, while Schedule 1 to the Form of Contract sets out a full set of Act-based "Additional Conditions" governing payment notices and due dates. Please could you clarify which is correct, as this affects the statutory payment framework applicable to the contract. | The reference in the Contract Data to the Housing Grants, Construction and Regeneration Act 1996 not applying is a drafting error and will be corrected. | 2026-07-15
2026-07-10 | Annex 3 - Pricing Schedule / Commercial | The planning permission confirms the development is liable for the Community Infrastructure Levy (CIL). Please could you confirm (a) the CIL liability amount applicable to this development, and (b) whether this cost is to be borne by the Authority or is to be included within the Contractor's tendered price. We would be grateful for responses to the above ahead of the clarification deadline. Given the direct bearing several of these points have on our assessment of the deliverability of this opportunity within the stated budget, we would appreciate confirmation as early as possible within the clarification period where feasible. | The Community Infrastructure Levy (CIL) liability associated with the development will be borne by the Authority and should not be included within the contractor's tendered price. Tenders should exclude any CIL costs from their pricing schedule. | 2026-07-13